## Server 2025
SierraLab Change control log
Last updated:
Controller:
Impact
ID | Description | Priority | Time | Initiator | Status | Date
C0.00 | What is the change requested? | H/M/L | ? days | Who requested change? | Complete/In Process/n/a | ??/??/??
1 | Setup Domain Controller | H | 1 day | Prof. Torres | Complete | 2026-02-11
2 | Add Admin and Users | H | 1 day | Prof. Torres | Complete | 2026-02-11
3
Guidelines for completion
ID: each request should have a unique code to identify it for easy reference.
Description: if the description is lengthy or complicated, then summarise here and refer to the particular change request document.
Priority: how important is the change listed? High priority should only be used for changes without which the project cannot be a success,
medium describes desirable changes, low describes trivial changes. Depending on the complexity of the project, may wish to add more categories, such as having an "E" for essential".
Impact: assess the probable impact of each change on the project definition and record the findings here. May have to consult with others to assess how the change would affect them.
When calculating the probable impact, remember to look at how any additional time, cost etc will affect the critical path of the project - need to account for the impact overall.
Initiator: record who requested the change.
Status: record whether the change is live, accepted, rejected or deferred.
Date: date of last update to the change control decision.

## Ubuntu
SierraLab Change control log
Last updated:
Controller:
Impact
ID | Description | Priority | Time | Initiator | Status | Date
C0.00 | What is the change requested? | H/M/L | ? days | Who requested change? | Complete/In Process/n/a | ??/??/??
1 | Joined to Doman | H | 1 day | Prof. Torres | Complete | 2026-02-11
Guidelines for completion
ID: each request should have a unique code to identify it for easy reference.
Description: if the description is lengthy or complicated, then summarise here and refer to the particular change request document.
Priority: how important is the change listed? High priority should only be used for changes without which the project cannot be a success,
medium describes desirable changes, low describes trivial changes. Depending on the complexity of the project, may wish to add more categories, such as having an "E" for essential".
Impact: assess the probable impact of each change on the project definition and record the findings here. May have to consult with others to assess how the change would affect them.
When calculating the probable impact, remember to look at how any additional time, cost etc will affect the critical path of the project - need to account for the impact overall.
Initiator: record who requested the change.
Status: record whether the change is live, accepted, rejected or deferred.
Date: date of last update to the change control decision.

## Sheet2
SierraLab Change control log
Last updated:
Controller:
Impact
ID | Description | Priority | Time | Initiator | Status | Date
C0.00 | What is the change requested? | H/M/L | ? days | Who requested change? | Complete/In Process/n/a | ??/??/??
1 | Joined to Domain | H | 1 day | Prof. Torres | Complete | 2026-02-11
Guidelines for completion
ID: each request should have a unique code to identify it for easy reference.
Description: if the description is lengthy or complicated, then summarise here and refer to the particular change request document.
Priority: how important is the change listed? High priority should only be used for changes without which the project cannot be a success,
medium describes desirable changes, low describes trivial changes. Depending on the complexity of the project, may wish to add more categories, such as having an "E" for essential".
Impact: assess the probable impact of each change on the project definition and record the findings here. May have to consult with others to assess how the change would affect them.
When calculating the probable impact, remember to look at how any additional time, cost etc will affect the critical path of the project - need to account for the impact overall.
Initiator: record who requested the change.
Status: record whether the change is live, accepted, rejected or deferred.
Date: date of last update to the change control decision.